## Plan
GROVA 1 : PROD - 18th / 19th June 2018
[5 empty] | ESTIMATE |  |  | ACTUAL
HLP | CM | Team | Indiv. | Description | Start | End | Duration | Start | End | Duration
1 |  | MW |  | Perform checksum for PROD servers Server Disk Space ¦ Free Memory Any other system related infrastructures
PRE- DEPLOYMENT TASKS - DXC
A1 | A7 - A9 | Network |  | Create VIP for Booking Reprice Servers | DONE
Create VIP for XS Agregator
Create VIP for HBG Reprice Stack
A2 | A10 | MW |  | Deploy Current version of HBG Adaptor + End Point to new Infra |  | Status- Existing version deployed
A3 | A11 | MW |  | Deploy current version of HBG Booking Engine to the new Infra |  | XWEB Aggregator - Version 16.0.68
A4 | A12 | MW |  | Build and add the 2 New XML Gateway Servers to the Load Balancer | Done | Added into Cluster - deployed existing prd version
A5 | A13 | MW |  | Disable on APACHE and Build POS and Web services (DJW and EJW and HJW) + XML API (AJW) |  | Plan to update during Evening BST hrs
A6 | A18 | AS |  | Set up new unicode test files
A7 | A14 | MW |  | XML Gateway: Puppet Updates |  | Scheduled at late night
OTHER PRE- DEPLOYMENT TASKS - Morning task
A8 | A1 | Ops |  | Server Health Check
A9 | A2 | Ops |  | COHERENCE Pre-Checks
A10 | A3 | Ops |  | COHERENCE : Cache back up NOVA ¦ HBG
| A4 | Ops |  | Validate Internal F5 URL for HBG | Status - Update A4 step with correct URL - Nxt step on Shawn to validate
| A5 | Ops | Shodan | Stop ATG BO Slot
| A6 | Ops | Shodan | Disable FITLPMRefresherScheduler job
| A15 | Ops | Subba | Run the Datagrid backup cron job
| A16 | Ops | Subba | Disable the Datagrid backup cron job
| A17 | Ops |  | DATAGRID : Take back up of active cache | NOVA
Capture check point time
|  |  |  | Upload datagrid backup into Passive nodes | 40 mins - start @ 3:30 - 4:30 backup and restore
| A18 | Ops |  | DATAGRID : HBG & NOVA Pre-checks
VALIDATE Production Sanity Jobs - search service jenkins automation jobs Legacy & Nova (Non HBG)
B1 | B1 | AS400 |  | Create & Deploy release packages | 3:30 | 0:30 | 4:00
B2 | B2 | Ops |  | Disable 1 FESB a1 (NOVA XML API) Deploy new DUA and restart | 3:45 | 0:15 | 4:00 |  |  |  | Deploy_FESB_PROD_HN_1
B3 - SANITY Testing on FESB A1 (Ops) |  |  |  |  | 4:10 | 0:05 | 4:15
B4 | B3 | Ops |  | Disable 7 FESB a2 to a8 deploy new DUA and restart | 4:15 | 0:15 | 4:30 |  |  |  | Deploy_FESB_PROD_HN_1
Deploy_FESB_PROD_HN_2
Deploy_FESB_PROD_HN_3
Deploy_FESB_PROD_HN_4
| B4 | Ops | [8 empty] | Deploy_FESB_PROD_HN_1
Deploy_FESB_PROD_HN_2
Deploy_FESB_PROD_HN_3
B5 - SANITY Testing on FESB A2 - A8 (Ops) |  |  |  |  | 4:45 | 0:05 | 4:50
B6 | B5 |  |  | BESB - Disable Nova Backend and deploy new code and retstart - B1 | 5:00 | 0:15 | 5:15 |  |  |  | Deploy_BESB_PROD
B7 - SANITY Testing on BESB - Booking Sanity ? -- Open with QA team |  |  |  |  | 5:00 | 0:15 | 5:15
OUTAGE Starts : Enable MAINTENANCE Page - 60 second pause : 05:00 BST
C1 |  | MW |  | Put up maintainence page for all VIPs 80 and 443 | 4:55 | 0:05 | 5:00
C2 | B6 | AS400 |  | Recycle CBS subsytems (ISERIES) | 5:05 | 0:15 | 5:20
C3 | B7 | MW |  | XML API Deployment | 5:25 | 0:05 | 5:30
C4 | B8 | MW |  | POS and Webservices Deployment | 5:40 | 0:05 | 5:45
| B9 | MW |  | EAN Deployment - 1.1.42
C5 | B10 | MW |  | XML Gateway Manual Deployment | 5:25 | 0:05 | 5:30
C6 | B11 | MW |  | HBG : Booking Gateway (lonshbgebs01a1 and a2) - uesb9 & uesb10 | 5:00 | 0:05 | 5:05
C7 | B12 | MW |  | HBG Price Engine Disable UESB 1 to 8 on lonshbgesb01a1, a2 and a3 | 5:10 | 0:05 | 5:15 | added a3 server
C8 | B13 | MW |  | HBG XWEB Aggregator - Enable lonshbgesb01 a4 to a6. Bring Up UESB 5 and 6 on lonsesbxsag01b1 | 5:25 | 0:05 | 5:30
C9 | B15 | MW |  | Deploy HBG DATAGRID Rolling restart | 5:00 | 0:45 | 5:45 |  |  |  | Deploy_HBG_Gar_Rolling_Quick_Cluster_PROD
C10 | B16 | MW |  | NOVA FESB: Enable traffic A1 to A8. Disable Traffic on A9 to A16 | 5:15 | 0:30 | 5:45
C11 | B14 | MW |  | Disable lonsesb01b2 and b3 and Enable lonsesb01b1 | 5:40 | 0:05 | 5:45
QA Sanity Testing : GR (Legacy POS), NOVA, HBG - Nova Clients (No Legacy HBG)
C12 |  | MW |  | Remove maintainence page for all VIPs 80 and 443 | 5:45 | 0:15 | 6:00
OUTAGE Finishes - Disable MAINTENANCE Page
[5 empty] | 6:00 | 1:00 | 7:00
D1 | B18/B19 | MW |  | POS and Webservices Deployment, (FJW, GJW, IJW) | 6:00 | 1:00 | 7:00 | Start at 7:00 - 10:30
D2 | B20 | MW |  | XML API Deployment (BJW and CJW) | 6:00 | 1:00 | 7:00
D3 |  | MW |  | HBG Price Engine & Xweb Adapter: Deploy and enable UESB 1 to 8 on lonshbgesb01a1 and a2 | 6:00 | 1:00 | 7:00
D4 | B21 | MW |  | GC Content Rolling Deployement | 6:00 | 1:00 | 7:00
D5 | B22 | MW |  | COHERENCE: Check cluster nodes = MACHINE SAFE | 6:00 | 0:05 | 6:05
D6 | B23 | MW |  | COHERENCE: Back up cache (2nd time) - disable cron job | 6:00 | 0:30 | 6:30
D7 | B24 | MW |  | DATAGRID - GAR_Rollling_Cluster | 6:30 | 0:45 | 7:15 |  |  |  | Datagrid_Gar_Rolling_Cluster_Node_PROD
D8 |  |  |  | DATAGRID - GAR Single Node | 7:00 | 0:30 | 7:30 |  |  |  | Deploy_Datagrid_Gar_Single_Node_PROD
D9 |  |  |  | DATAGRID - WebWar |  |  | 7:45 |  |  |  | Deploy_Datagrid_WebWar_PROD
D10 | B25 | MW |  | NOVA FDL Deployment (Full Data Loader) |  |  | 8:00 |  |  |  | Deploy_FullDataLoader_PROD
D11 | B26 | MW |  | DDL Deployment (Dynamic Data Loader) |  |  | 8:00 |  |  |  | Deploy_DynamicDataLoader_PROD
D12 | B27 | MW |  | PNR Deployment - Roll deployment |  | 0:30 | 8:30 |  |  |  | Deploy_PNR_PROD
| B28 |  |  | FE Search Service Deployment |  |  | 480:00 | 20 |  |  | Deploy_FESearchService_PROD
D13 | B29.1 B29.2 | MW |  | NOVA FESB: Deploy, restart and enable Traffic on A9 to A16 |  |  | 8:45
Deploy_FESB_PROD_HN_1
Deploy_FESB_PROD_HN_2
Deploy_FESB_PROD_HN_3
Deploy_FESB_PROD_HN_4
Deploy_FESB_PROD_HN_1
Deploy_FESB_PROD_HN_2
Deploy_FESB_PROD_HN_3
Deploy_FESB_PROD_HN_4
D14 | B30 | MW |  | BESB Deployment (b2 & b3) |  |  | 9:00 |  |  |  | Deploy_BESB_PROD
| B31 | MW |  | FESB: Agoda Deployment (b2) - Downloadable cache (Rolling deployment) |  |  |  | 10 |  |  | Deploy_FESB_PROD_HN_1
| B32 | MW |  | FESB: Agoda Deployment (b3) | [6 empty] | Deploy_FESB_PROD_HN_1
| B33 | MW |  | FESB: Agoda Deployment (b1) | [6 empty] | Deploy_FESB_PROD_HN_1
| B34 | MW |  | FESB: Agoda Deployment (b4) | [6 empty] | Deploy_FESB_PROD_HN_1
D15 | B35 | MW |  | DATASYNC Deployment |  |  | 9:15 |  |  |  | Deploy_dataSync_PROD
D16 | B36 | MW |  | Static DATASYNC Deployment |  |  | 9:30 |  |  |  | Deploy_Static_Data_Replication_PROD
D17 | B37 | MW |  | HBG: PNRWEB Deployment | [6 empty] | Deploy_HBG_PNRWEB_PROD
D18 | B38 | MW |  | HBG: Cohql Deployment |  |  | 9:45 |  |  |  | Deploy_HBG_COHQL_PROD
D25 | B39 | MW |  | CE Deployment |  |  | 23:30
POST DEPLOYMENT STEPS
D21 | C1 | MW |  | Deploy HBG FDL | 8:30 |  | 9:00 |  |  |  | Deploy_HBG_Full_Data_Loader_PROD
D22 |  | MW |  | Update cron job | 8:30 |  | 9:00
D23 |  | MW |  | Update JDK version
D24 |  | MW |  | HBG Cache Content - HBG Datagrid -- new cache "gtaRoomMapping" Validation
SANITY TESTING : GR, NOVA, HBG
GR Regression Testing

## Info
RFC | http://jira.emea.kuoni.int/browse/RFC-28068
Implementation Plan | http://confluence.emea.kuoni.int/display/RM/GROVA1+-+PRODUCTION+-+RELEASE+-+Deployment+1-4
PROD Sanity Jobs | http://longscm01n:9090/job/HotelSearch_PROD/